# MWPSOL-166: Home Claims - RAID

- 1. Risks Log

    - Mitigation for DirectQuery Mode Limitations: ￼

  - Summary Table for Risk Status

- 2. Assumptions Log

  - Summary Table for Assumption Status

- 3. Issues Log

  - Summary Table for Issue Status

- 4. Decision Log

  - Summary Table for Decision Status

The RAID table below is ongoing and not exhaustive. As new risks, assumptions, issues, or decisions are identified during the project, they will be recorded here.

## 1. Risks Log

|  | Likelihood | Impact | Risk ID | Risk Description | Mitigation Plan | Risk Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | LOW | MEDIUM | R-1 | Home Assessors using non-compliant devices other than the tested Surface Pro tablet may experience issues, as the custom app is only confirmed and tested to be mobile responsive on Surface Pro (see assumption ID A-7). | Educate Home Assessor to use an approve RAC Surface Pro tablet. Do not take their personal device to on-site inspection and use the custom app from their personal device. | Open |
| 2 | HIGH | HIGH | R-2 | Power Canvas Apps has delegation limits (e.g. 2,000 records) when querying large datasets. If not handled correctly, this can lead to incomplete data being displayed or processed within the app, particularly for search or aggregation scenarios (though search is out of scope for MVP, future iterations would face this). | Development: - Implement Power Apps functions that are delegable to Dataverse (e.g. leverage Filter(), LookUp(), Sort(), StartsWith() functions) when searching Dataverse table and displaying the found records into search result grid in the app’s search screen. Avoid non-delegable functions on large datasets. - The default number of records canvas app can retrieve is 500 records. It can increase this limit to 2,000 records in the canvas app settings. Dataverse Views - Create some custom views for Dataverse table. Examples include: - View Recent Claims from the last 30 days - Show claim records that are 30 days or less from today. | Open |
| 3 | HIGH | HIGH | R-3 | Users attempting to browse very large SharePoint document libraries directly in SharePoint might experience performance issues or incomplete results if views are not optimized to find PDF files. This is due to SharePoint document libraries have a document view threshold (typically 5,000 items) that can impact the display of large numbers of documents in a single view. | Document Views & Index - Create some custom views for the doc library: - View Recent Claims from the last 30 days - Show claim records that are 30 days or less from today. - View old PDF files that are older than 30 days. - Create a new indexed view on column “Claim Number” | Open |
| 4 | HIGH | MEDIUM | R-4 | Dataverse operates on daily API entitlement limits per day depending on the types of licenses being purchased. - Power Automate Premium: ~40,000 requests/day per licensed user - Power Apps per app plan: ~6,000 requests/day per licensed user This includes all types of Dataverse operations: create, read, update, delete (CRUD). | Optimization: Design Power Automate flows and Power Apps to minimize unnecessary API calls. Batch operations where possible. | Open |
| 5 | HIGH | HIGH | R-5 | Limitations with Power BI Pro Licence If PBI report connects to Dataverse using import mode, there are inherent limitations with Import mode (regardless of the data source). - Dataverse imported into Power BI is a snapshot at a specific point in time. It's not real-time. To get the latest data, the dataset needs to be refreshed manually or on a schedule. - Dataflow Refresh Limits: Dataflows operating in a workspace backed by a Power BI Pro license are subject to an 8-refresh-per-day limit. - Report Dataset Size Limits: The Power BI report's dataset (after importing data from the Dataflow) must remain under the 1 GB limit for Power BI Pro If PBI report connects to Dataverse using DirectQuery mode: - Near Real-Time Data: Visuals query the Dataverse database directly, so the data is always up to date. Therefore, the 8-refresh per day limit is not applicable. - Ideal when the Dataverse data volume is very large and exceeds the 1 GB import limit - 1 million Row Limit: A single query from a visual cannot return more than 1 million rows from Dataverse. Resource - What licenses do you need to use dataflows - Power Query ¦ Microsoft Learn - Creating a dataflow - Power BI ¦ Microsoft Learn | For the initial next phase (post-MVP), start with DirectQuery. This provides the most "real-time" view of the data without the need to manage data refreshes or worry about the 1 GB dataset size limit. #### Mitigation for DirectQuery Mode Limitations: ￼ - Design for Aggregation: Design reports to show aggregated summaries, KPIs, and charts. Avoid creating large table visuals that attempt to display thousands of rows. - Filter Data: Only import a relevant date range of data (e.g., the last 24 months) instead of the entire history. Older data can be archived. - Effective Filtering: Implement slicers and filters so that users can narrow down their queries to specific date ranges, regions, or service providers. This ensures the queries sent to Dataverse are small and fast. - Optimize the Data Model: While the Dataverse model we designed is already well-structured, ensure that any DAX measures written for the report are efficient and perform calculations on aggregated data where possible. - Educate Report Consumers: Train leaders on how to use the report effectively with filters, rather than trying to export the entire underlying dataset. Summary Monitor Dataset Size: Regularly monitor the size of the .pbix file and the dataset in the Power BI Service. Plan for a move to a Premium license if the dataset is projected to exceed larger size. | Open |

### Summary Table for Risk Status

| Status | Meaning |
| --- | --- |
| Open | The risk has been identified and logged, but no mitigation action has started yet |
| Under Review | The risk is being analysed or assessed for likelihood, impact, and responses. |
| Mitigating | Actions to reduce the likelihood or impact of the risk has actively been implemented. |
| Escalated | The risk has become critical or cannot be managed at the current level and has been escalated to higher management. |
| Accepted | The risk is acknowledged, but no action will be taken. |
| Closed | The risk is no longer relevant, has been fully mitigated, or the event has occurred and been dealt with. |
| Occurred | The risk event has happened and is now being managed as an issue or will resolve the risk (sometimes moved to the Issues section). Once risk has been resolved, the status is closed. |

## 2. Assumptions Log

|  | Assumption ID | Date Reviewed | Assumption Description | Status |
| --- | --- | --- | --- | --- |
| 1 | A-1 | 12 Jul 2025 | The minimum number of photos required per question/section for comprehensive visual evidence is assumed to be at least 3 photos taken. However, this assumption shall later be validated with decision ID DEC-1. | Open |
| 2 | A-2 | 12 Jul 2025 | The custom app's visual design (e.g. colours, fonts) shall align with RAC's branding approved UI/UX guidelines. | Validated |
| 3 | A-3 | 12 Jul 2025 | Edge browser (latest SOE version) is installed and maintained as the standard and primary browser on all RAC-issued Surface Pro tablets used by home assessors within the Standard Operating Environment (SOE). No other web browser desktops are installed on the Surface Pro tablet. | Open |
| 4 | A-4 | 12 Jul 2025 | Business hours start from 7AM - 5PM AWST, Mon-Fri. However, this needs to be validated with the stakeholders on what time Home Assessor start work. | Open |
| 5 | A-5 | 12 Jul 2025 | M365 E5 plan license will already be assigned to the Home Assessors and Home Assessing Team. | Validated |
| 6 | A-6 | 12 Jul 2025 | No existing data migration to be imported into the Dataverse will exists. | Validated |
| 7 | A-7 | 12 Jul 2025 | Only the Surface Pro tablet will be tested for the custom app mobile responsiveness. This is because the Home Assessor will be using this tablet model. No other tablet devices will be tested with the custom app. This will raise a potential risk ID R-1. | Open |
| 8 | A-8 | 17 Jul 2025 | Solution for RACI will take into considerations how it can later be easily separated from RAC group as part of RACI acquisition by IAG. | Open |

### Summary Table for Assumption Status

| Status | Description |
| --- | --- |
| Open | The assumption is newly recorded and has not yet been validated or tested. |
| Under Review | The assumption is being investigated or discussed for validation. |
| Validated | The assumption has been confirmed as true and is accepted as a basis for planning/decision-making. |
| Invalidated | The assumption has been proven false and may require action or a change in plan. |
| Closed | If the assumption is no longer relevant or superseded, update the status and the review date it was closed (e.g., because it has been addressed, superseded, or is moot). |
| Escalated | The assumption is causing a risk or issue and has been escalated for management attention. |

## 3. Issues Log

| ID | Date Raised | Issue Description | Dependency | Impact | Severity | Priority | Mitigation Plan | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| I1 |  |  |  |  |  |  |  |  | Open |

### Summary Table for Issue Status

| Status | When to Use |
| --- | --- |
| Open | When the issue is first identified and logged. |
| Under Investigation | When root cause analysis or impact assessment is underway. |
| Action in Progress | When corrective or mitigating actions are being implemented. |
| Escalated | When the issue is severe and requires higher-level intervention or decision. |
| Resolved | When a fix has been applied but may need monitoring or verification. |
| Closed | When the issue is fully resolved. |
| Deferred | When the issue will be addressed later. |

## 4. Decision Log

|  | Decision ID | Date | Decision Owner | Decision | Status | Outcome |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | MVP Phase |  |  |  |  |  |
| 2 | DEC-0 | 12 Jul 2025 | Engineering Team | Submit this solution intent to the engineering team for their review. Given the dealing with customer’s sensitive data, a review by the Engineering Team is essential to ensure alignment, technical feasibility, and adherence to standards. ￼ | Open | TBD (To be Decided) |
| 3 | DEC-1 | 12 Jul 2025 | Home Assessing Team & Home Assessor | Validate the exact minimum number of photos required per question/section for assessment in the custom app. | Open | TBD |
| 4 | DEC-3 | 12 Jul 2025 | Home Assessing Team | Validate the PDF formats and target SharePoint storage location with the stakeholders: - Where is the existing or new target SharePoint document library location that will store the PDF copy that was generated and uploaded by the custom app. - What does the format and layout of the PDF content look like for considerations such as: - Header and footer. - Company logo. - Terms and conditions. - layout of the questions, answers and any attached photo. | Open | TBD |
| 5 | DEC-5 | 13 Jul 2025 | Home Assessing Leaders | Validate the following licencing requirements: - How many end-users and who will need access to the custom app? - How many end-users and who will need owner’s access to PBI reporting? - Approval to purchase additional new licences for a dedicated service account and end-users? (Read section 3.6.3 for more details) | Open | TBD |
| 6 | DEC-7 | 13 Jul 2025 | Home Assessing Team | Validate which important metadata fields from the Dataverse table will be replicated as new columns in SharePoint document library to allow quick search and find the PDF files end-user are looking for. Example one key fields to use is Claim Number. | Open | TBD |
| 7 | DEC-8 | 13 Jul 2025 | - Home Assessing Team & Leaders - Field Assessor - Modern Workplace | - Validate user training requirements. - Provide user guide manual. | Open | TBD |
| 8 | Future Phase |  |  |  |  |  |
| 9 | DEC-2 | 12 Jul 2025 | Home Assessing Leaders | Validate the content for PBI reports with stakeholders. The goal of PBI report is to improve reporting and performance management. The SP QA requirements.xlsx contains numerous fields that are direct inputs for calculating potential KPIs such as: - Ratings: There are multiple dropdowns for ratings (Poor/Fair/Good) such as "Quality, workmanship and materials rating", "Satisfaction Overall Rating", "Trades Rating", "Communication rating", "Workmanship rating", and "Cleanliness rating". These directly lend themselves to calculating "average scores." - Yes/No Questions: Fields like "Correct Claim Determination?", "Costing Fair & Reasonable?", "Quality issue identified?”, and "Workmanship Rectifications Needed?" are suitable for deriving "compliance rates" or identifying areas of non-compliance. Validate the access permission for PBI reports such as: - Will PBI report be published to a new or existing workspace in the Power BI Service? - Who will be the owners of PBI reports with dashboard? - Who is the list of end-users that will need access to the PBI Workspace? Validate the PBI licensing: - How many and who are the users who will become the report owners to edit, publish and share the PBI reports to a workspace for their Home Claim Team. - Read appendix 1 for more details about which PBI licence to utilised for the end-users. | Open | TBD |
| 10 | DEC-4 | 13 Jul 2025 | Modern Workplace | - To validate and access turning on built-in Dataverse audit logging in the dedicated Power Platform environment where the solution will be deployed. - To decide on the naming convention for the new service account and the dedicated Power Platform environments. - Raise a change request ticket for environment changes to be approved by CAB. | Open | TBD |
| 11 | DEC-6 | 13 Jul 2025 | Home Assessing Team | Data Migration Strategy (if applicable): Validate if there's an existing audit data from an Excel that needs to be migrated into Dataverse, including plans for data extraction and transformation. | Closed | No data migration is needed |

### Summary Table for Decision Status

| Status | Meaning |
| --- | --- |
| Proposed | The decision has been suggested but not yet discussed or agreed upon. |
| Under Review | The decision is being considered, discussed, or analysed by stakeholders. |
| Approved | The decision has been agreed upon and formally accepted by the relevant authority/group. |
| Rejected | The decision was considered but not accepted or implemented. |
| Implemented | The approved decision has been put into action. |
| Deferred | The decision has been postponed for consideration later. |
| Superseded | The decision has been replaced by a newer decision and is no longer in effect. |
| Closed | The decision process is complete, and no further action is required. |